## Slide 1: HREDI Annual Progress Report 2023
Feb 2024

## Slide 2: HREDI Strategy 2023 – 2027
Developed and approved by the University of Limerick's Human Rights Equality Diversity and Inclusion Committee using templates developed by the Irish Universities Association.
The development & stakeholder consultation was facilitated by Niall Crowley of Value Labs.
Human Rights Equality Diversity & Inclusion Strategy | University of Limerick (ul.ie) Launched on Dec 12th following broad consultation and development by dedicated working group throughout the year.
5 core values
  Social Justice, Empowerment, Inclusivity, Agency & Respect.
Aims to embed Assess, Address, Report across University function.
Integrates existing targeted action plans to create a portfolio of actions
Supported by evidence base & implementation process.
Next Steps: Enabling Implementation

## Slide 3: Irish Human Rights & Equality Commission: System
Irish Human Rights and Equality Commission has developed a system to monitor the performance of public bodies in relation to the requirements under Section 42 of the Irish Human Rights and Equality Commission (IHREC) Act 2014 (the Public Sector Equality and Human Rights Duty). This project has been carried out in line with our monitoring and assistance role under Section 42.
Section 42(2) of this Act requires public bodies to undertake a three-step process of self-assessment and reporting. A public body must set out an assessment in its strategic plan of the human rights and equality issues it believes to be relevant to its functions and purpose, and the policies, plans and actions proposed, or in place, to address these issues. This must be done while having regard to its size and the resources available to it. A public body must then report on progress against these actions in its annual report (or equivalent). Both the assessment of the issues, the related actions, and the report on progress against these actions, must be publicly accessible.

## Slide 4
Chart: HEA Progress Report Indicator Status By Section
| Race Equality | HEI-Leadership Commitments | Barometer
No update required (ESVH Reporting) | 2
Requirement next year | 4
No update required (Working Act Provisions) | 1
No update required (Gender Pay Gap Reporting) | 1
Consulting with relevant area | 3 | 2 | 7
Orange some progress - In progress, Further work needed | 4 | 7 | 12
Red little progress - Not started | 4 | 11
Yellow good progress - In progress, Further work needed | 1 | 3 | 2
Green very good progress - Established practice, no further work needed | 1

## Slide 5
Chart: Barometer Theme By Indicator Status
| Career Development | Data Capture, Analysis And Reporting | Intersectionality | Leadership | Org Culture | Precarity | Teaching & Learning, Research & Quality Assurance
Consulting with relevant area | 1 | 1 | 5
No update required (ESVH Reporting) | 2
No update required (Gender Pay Gap Reporting) | 1
No update required (Working Act Provisions) | 1
Orange some progress - In progress, Further work needed | 4 | 1 | 2 | 1 | 2 | 2
Red little progress - Not started | 3 | 2 | 1 | 2 | 1 | 2
Requirement next year | 4
Yellow good progress - In progress, Further work needed | 1 | 1

## Slide 6: HREDI Implementing Actions
HEA Barometer
6 actions
Leadership & Governance
Integrating
5 actions
Monitoring
2 actions
6 actions
Aligning
3 Actions
Training
1 + HEA Barometer
Advising
1 action

## Slide 7: Actions on Training:
Action | Priority | Update
Briefing video and training sessions to be developed * | High | 
* Training on Implementing the address step needed for Barometer Stage actions

## Slide 8: Actions that impact HEA Barometer:
Action | Priority | Update
Integrate HREDI into University Strategy Development | High | Contact made
Policy Development framework: Training on the Duty, in particular the address step | High | Training in need of development
Quality Review Process: Training on the Duty, in particular the address step | High | Training in need of development
Policy Development Framework updated to include HREDI requirements in particular the address step | High | 
Integrate HREDI into Quality Review Process | Medium | 
Develop system to record assess address tracking system | Medium | Initial steps

## Slide 9: Actions to strengthen Leadership & Governance:
Action | Priority | Update
Familiarisation sessions on the Duty for GA, Exec & Mgmt Council. Faculty SciEng, EHS updated. KBS & EHS to be completed | High | Nearing Completion
Executive Committee agenda to include public sector duty as regular item on agenda. | High | Quick Win
Management Council agenda to include duty as regular item on agenda. | High | Quick Win
HREDI Steering Committee to review progress | Medium | Starts Today
Local EDI committees briefing and exchange | Medium | -
Integrate HREDI strategy, AS & Race Equality Action Plan as standing Item on dept Agendas | Medium | -

## Slide 10: Actions to align existing action plans:
Action | Priority | Update
Integrate HREDI into Athena Swan Action Plan | Medium | Initial Steps
Integrate HREDI into Race Equality Action Plan | Medium | -
Integrate HREDI into Consent framework Action Plan | Medium | -

## Slide 11: Actions to Monitor Progress:
Action | Priority | Update
Output and outcome indicators to be developed to monitor progress to implement the Duty | High | -
Performance indicators to be developed and monitored for address step of Public sector duty | High | -

## Slide 12: Action to Advise:
Action | Priority | Update
Review and Feedback on collaborative agreements draft policy | High | -
Other actions include integrating HREDI into
PDRS
Staff Induction
1st Seven Weeks
Marketing & Communications

## Slide 13: Quick Wins & High Priority Actions
Quick Wins
Added to Exec & Mgmt Council As regular agenda Item
University Strategy
Development started
Define monitoring indicators
Policy & Quality Processes
Training & Promotion Material
Development needed
Indicators
Collaborative Policy Review
HEA Barometer
Added to Risk Register
Add HREDI Strategy to all dept agendas
IHREC introduction module online
https://www.ihrec.ie/our-work/public-sector-duty/training-tools-and-resources/
https://www.ihrec.ie/our-work/public-sector-equality-and-human-rights-duty-faq/implementing-the-duty-pilot-case-studies/